## Home
Document summary |  | Project information |  | Table of contents | Description of the sheet content
Document name | Work breakdown structure (WBS) & Gantt chart | Start date | 2025-04-23 09:00 | WBS | Breakdown of the tasks during the project
Document Owner | Abderrazaq MAKRAN | End date | 2025-06-20 | Gantt chart | Prevision of the schedule which will be used during the project
Creation date | 2025-04-23 | Total duration | 57.625
Last updated | 2025-05-16 | Days elapsed | 57.625
|  | Days to go | 0
|  | Time progress | 100%
Schedule Legend
Gantt chart: Should be done during this project Actual schedule: Has been done during this project
Gantt chart: Deadline of the delivery

## WBS
ID | Category | Priority | Task | Assignee(s) | Status | Deadline
P | Planning |  |  |  | Done
P1 | Planning | High | Project kick-off & framing | All team members | Done | 2025-04-22
P2 | Planning | High | Project Charter | Abderrazaq | Done | 2025-04-23
P3 | Planning | High | Task definition | Abderrazaq | Done | 2025-04-24
P4 | Planning | High | KPIs | Abderrazaq | Done | 2025-04-24
P5 | Planning | High | Risk anticipation & management | Abderrazaq | Done | 2025-04-24
P6 | Planning | High | Schedule creation | Abderrazaq | Done | 2025-04-25
D | Design
D1 | Design | Medium | Graphical charter | Quentin | Done | 2025-05-01
D2 | Design | Medium | User journey roadmap creation | Quentin | Done | 2025-05-02
D3 | Design | High | Pages mock-ups | Quentin | Done | 2025-05-05
A | App
A1 | App | High | Define Bubble Data Types, Option Sets & CSV | Manech | Done | 2025-05-08
A2 | App | Optional | Splash Screen Design/Impl. | Quentin | Done | 2025-05-13
A3 | App | High | Onboarding flow (3 steps) | Pierre | Done | 2025-05-15
A4 | App | Medium | Functional Specification | Quentin | Done | 2025-05-16
A5 | App | High | Home page (search + categories) | Pierre | Done | 2025-05-16
A6 | App | High | ProductCard component | Abderrazaq | Done | 2025-05-20
A7 | App | High | Recommendation component | Pierre | Done | 2025-05-21
A8 | App | High | Profile page (user settings) | Manech | Done | 2025-05-22
A9 | App | Medium | Favorites page | Abderrazaq | Done | 2025-05-23
A10 | App | High | Translation system (FR/EN toggle) | Pierre | Done | 2025-05-26
A11 | App | Low | “Remember last viewed” search feature | Manech | Done | 2025-05-27
A12 | App | Medium | Technical Specification | Manech | Done | 2025-05-28
A13 | App | High | Filtering by tag & main meat/color/type | Abderrazaq | Blocked | 2025-05-30
A14 | App | High | Recommendation Page | Abderrazaq | Done | 2025-05-31
A15 | App | High | Product listing/all-products pages | Abderrazaq | Done | 2025-06-04
A16 | App | High | Tag system for all product types | Abderrazaq | Done | 2025-06-05
A17 | App | High | Import and optimize media (image resize) | Abderrazaq | Done | 2025-06-10
A18 | App | High | Database import (CSV for 30/10/10) | Manech | Done | 2025-06-11
Q | Quality Assurance
Q1 | Quality Assurance | Medium | Test Plan | Evan | Done | 2025-06-06
Q2 | Quality Assurance | Medium | Github templates | Abderrazaq | Done | 2025-06-12
Q3 | Quality Assurance | Medium | Project Charter Review | Evan | Done | 2025-06-13
Q4 | Quality Assurance | Medium | Functional Review | Evan | Done | 2025-06-13
Q1 | Quality Assurance | Medium | Technical Review | Evan | Done | 2025-06-14
Q2 | Quality Assurance | Medium | Code & User Manual | David | Done | 2025-06-16
Q3 | Quality Assurance | High | Code reviewing | Evan | Done | 2025-06-16
Q4 | Quality Assurance | Optional | README | Abderrazaq | Done | 2025-06-16
Q1 | Quality Assurance | Medium | User Manual Review | Evan | Done | 2025-06-16
Q2 | Quality Assurance | High | Testing phase | Evan | Done | 2025-06-17
C | Closure
C1 | Closure | High | Oral presentation preparation | All team members | Done | 2025-06-19
C2 | Closure | High | Final Pitch | All team members | Done | 2025-06-20
C3 | Closure | Low | Post-Mortem | All team members | Done | 2025-06-21

## Gantt chart
[6 empty] | Week 1 |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  | Week 9
 | time axis 2025-04-22 to 2025-06-21
ID | Task | Main assignee | Start date | Expected End | Deadline
P
P1 | Project kick-off & framing | All team members | 2025-04-22 | 2025-04-22 | 2025-04-22 | bar: 2025-04-22
P2 | Project Charter | Abderrazaq | 2025-04-23 | 2025-04-23 | 2025-04-23 | bar: 2025-04-23
P3 | Task definition | Abderrazaq | 2025-04-24 | 2025-04-24 | 2025-04-24 | bar: 2025-04-24
P4 | KPIs | Abderrazaq | 2025-04-23 | 2025-04-24 | 2025-04-24 | bar: 2025-04-23 to 2025-04-24
P5 | Risk anticipation & management | Abderrazaq | 2025-04-23 | 2025-04-24 | 2025-04-24 | bar: 2025-04-23 to 2025-04-24
P6 | Schedule creation | Abderrazaq | 2025-04-23 | 2025-04-25 | 2025-04-25 | bar: 2025-04-23 to 2025-04-25
D
D1 | Graphical charter | Quentin | 2025-05-01 | 2025-05-01 | 2025-05-01 | bar: 2025-05-01
D2 | User journey roadmap creation | Quentin | 2025-05-01 | 2025-05-02 | 2025-05-02 | bar: 2025-05-02
D3 | Pages mock-ups | Quentin | 2025-05-02 | 2025-05-05 | 2025-05-05 | bar: 2025-05-02 to 2025-05-05
A
A1 | Define Bubble Data Types, Option Sets & CSV | Manech | 2025-05-05 | 2025-05-08 | 2025-05-08 | bar: 2025-05-05 to 2025-05-08
A2 | Splash Screen Design/Impl. | Quentin | 2025-05-13 | 2025-05-13 | 2025-05-13 | bar: 2025-05-13
A3 | Onboarding flow (3 steps) | Pierre | 2025-05-14 | 2025-05-15 | 2025-05-15 | bar: 2025-05-14 to 2025-05-15
A4 | Functional Specification | Quentin | 2025-05-02 | 2025-05-14 | 2025-05-16 | bar: 2025-04-23 to 2025-05-16
A5 | Home page (search + categories) | Pierre | 2025-05-12 | 2025-05-16 | 2025-05-16 | bar: 2025-05-12 to 2025-05-16
A6 | ProductCard component | Abderrazaq | 2025-05-15 | 2025-05-20 | 2025-05-20 | bar: 2025-05-15 to 2025-05-20
A7 | Recommendation component | Pierre | 2025-05-19 | 2025-05-21 | 2025-05-21 | bar: 2025-05-19 to 2025-05-21
A8 | Profile page (user settings) | Manech | 2025-05-20 | 2025-05-22 | 2025-05-22 | bar: 2025-05-20 to 2025-05-22
A9 | Favorites page | Abderrazaq | 2025-05-16 | 2025-05-23 | 2025-05-23 | bar: 2025-05-16 to 2025-05-23
A10 | Translation system (FR/EN toggle) | Pierre | 2025-05-23 | 2025-05-26 | 2025-05-26 | bar: 2025-05-23 to 2025-05-26
A11 | “Remember last viewed” search feature | Manech | 2025-05-27 | 2025-05-27 | 2025-05-27 | bar: 2025-05-27
A12 | Technical Specification | Manech | 2025-04-23 | 2025-05-16 | 2025-05-28 | bar: 2025-04-23 to 2025-05-28
A13 | Filtering by tag & main meat/color/type | Abderrazaq | 2025-05-28 | 2025-05-30 | 2025-05-30 | bar: 2025-05-28
A14 | Recommendation Page | Abderrazaq | 2025-05-26 | 2025-05-31 | 2025-05-31 | bar: 2025-05-26 to 2025-05-28
A15 | Product listing/all-products pages | Abderrazaq | 2025-06-03 | 2025-06-04 | 2025-06-04 | bar: 2025-06-03 to 2025-06-04
A16 | Tag system for all product types | Abderrazaq | 2025-06-04 | 2025-06-05 | 2025-06-05 | bar: 2025-06-04 to 2025-06-05
A17 | Import and optimize media (image resize) | Abderrazaq | 2025-06-06 | 2025-06-10 | 2025-06-10 | bar: 2025-06-06 to 2025-06-10
A18 | Database import (CSV for 30/10/10) | Manech | 2025-06-10 | 2025-06-10 | 2025-06-11 | bar: 2025-06-10 to 2025-06-11
Q
Q1 | Test Plan | Evan | 2025-06-02 | 2025-06-06 | 2025-06-06 | bar: 2025-06-02 to 2025-06-06
Q2 | Github templates | Abderrazaq | 2025-06-10 | 2025-06-12 | 2025-06-12 | bar: 2025-06-12
Q3 | Project Charter Review | Evan | 2025-06-13 | 2025-06-13 | 2025-06-13 | bar: 2025-06-13
Q4 | Functional Review | Evan | 2025-06-13 | 2025-06-13 | 2025-06-13 | bar: 2025-06-13
Q1 | Technical Review | Evan | 2025-06-14 | 2025-06-14 | 2025-06-14 | bar: 2025-06-13
Q2 | Code & User Manual | David | 2025-05-05 | 2025-06-16 | 2025-06-16 | bar: 2025-05-05 to 2025-06-16
Q3 | Code reviewing | Evan | 2025-06-16 | 2025-06-16 | 2025-06-16 | bar: 2025-06-13 to 2025-06-16
Q4 | README | Abderrazaq | 2025-06-16 | 2025-06-16 | 2025-06-16 | bar: 2025-06-13 to 2025-06-16
Q1 | User Manual Review | Evan | 2025-06-16 | 2025-06-16 | 2025-06-16 | bar: 2025-06-13 to 2025-06-16
Q2 | Testing phase | Evan | 2025-06-10 | 2025-06-17 | 2025-06-17 | bar: 2025-06-10 to 2025-06-17
C
C1 | Oral presentation preparation | All team members | 2025-06-13 | 2025-06-18 | 2025-06-19 | bar: 2025-06-13 to 2025-06-19
C2 | Final Pitch | All team members | 2025-06-20 | 2025-06-20 | 2025-06-20 | bar: 2025-06-20 to 2025-06-21
C3 | Post-Mortem | All team members | 2025-06-21 | 2025-06-21 | 2025-06-21 | bar: 2025-06-21

## KPIs
|  | Week 1 (4/22/2025 - 4/25/2025) |  | Week 2 (4/28/2025 - 5/2/2025) |  | Week 3 (5/5/2025 - 5/9/2025 ) |  | Week 4 (5/12/2025- 5/16/2025 ) |  | Week 5 (5/19/2025 - 5/23/2025) |  | Week 6 (5/26/2025 - 5/28/2025) |  | Week 7 (6/2/2025- 6/6/2025) |  | Week 8 (6/10/2025 - 6/13/2025) |  | Week 9 (6/16/2025 - 6/20/2025)
Category | Name | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual
Documents | Functional Specifications | 25% | 15% | 75% | 70% | 90% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Documents | Technical Specifications | 10% | 0% | 25% | 10% | 50% | 30% | 75% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10% | Test Plan | 10% | 0% | 15% | 0% | 20% | 0% | 20% | 0% | 45% | 25% | 55% | 40% | 100% | 100% | 100% | 100% | 100% | 100%
Documents | Management (Planning, KPIs, Risks, Documents...) | 30% | 25% | 60% | 50% | 80% | 75% | 80% | 75% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Software | Define Bubble Data Types, Option Sets & CSV | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Software | Splash Screen Design/Impl. | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Software | Onboarding flow (3 steps) | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Software | Home page (search + categories) | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Hardware | ProductCard component | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Recommendation component | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Profile page (user settings) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Favorites page | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Translation system (FR/EN toggle) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| “Remember last viewed” search feature | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Filtering by tag & main meat/color/type | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Recommendation Page | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Product listing/all-products pages | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
| Tag system for all product types | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
| Import and optimize media (image resize) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100%
| Database import (CSV for 30/10/10) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
Final Product Completion |  | 0% | 0% | 0% | 0% | 6.25% | 6.25% | 33.12% | 32.81% | 56.25% | 55.62% | 75% | 75% | 90.62% | 90.62% | 100% | 100% | 100% | 100%
Total Project Completion | Total Project Completion | 3.947% | 2.105% | 9.211% | 6.842% | 17% | 14.25% | 40.25% | 39% | 62% | 60.5% | 77.75% | 77% | 92.5% | 92.5% | 100% | 100% | 100% | 100%
HR
HR

## TPC
Week | Expected | Actual
Week 1 | 4% | 2%
Week 2 | 9% | 7%
Week 3 | 17% | 12%
Week 4 | 40% | 35%
Week 5 | 62% | 57%
Week 6 | 78% | 73%
Week 7 | 93% | 80%
Week 8 | 100% | 100%
Week 9 | 100% | 100%